## READ-ME
Review of the following documents:
OETCS_API Requirements_v1.2
OETCS_API Requirements_appendix_application_layer_v1.0
OETCS_API Requirements_appendix_functional_data_dictionary_v1.0
Name | Date | Modifications
N. Boverie | 12 may 2014 | All
N. Boverie | 3 july 2014 | See comment sheet (modifications for OETCS_API Requirements_v1.3)
Meaning of the comment reply :
Reply Status
Accepted | It means that a change of the API document is to be analysed by Alstom. It is not a commitment for a change.
Rejected | It means that the Alstom position is to achieve no change to the document.
Clarify | It means that the comment is not well understood by Alstom. The comment has to be clarified.
TBD | To be defined / To be discussed
If the reply status is "Rejected"
Design Choice | The Alstom solution is right. It is a matter of choice.
Out of Scope | The subject is out of the API scope
Misunderstanding | The reviewer has not well understood and the API document is supposed to be good enough.
Answer provided | The reviewer has asked a question and the answer is provided
TOPIC
document | Only an API documentation mistake or improvement. (Form)
SW | The comment is about the Software coding of the API (static aspect) : language, way to transfer in/out data (pointers, call of procedure/functions, etc …), …
Platform | The comment is about the platform behaviour (dynamic aspect) : cycle principle, performance, asynchronous peripheral boards, etc…
System architecture | The comment is about the allocation of functions between the ETCS application, the basic SW, the peripherals, etc…

## All
Number | Who | § | Comment | Reply status : - Accepted - Rejected - Clarify - TBD | If Rejected: - Design Choice - out of scope - Misunderstanding - Answer provided | Defect (Y/N) | Topic: - Document - SW - Platform - System Architecture | Reply (Alstom) | modification achieved in OETCS_API Requirements_v1.3 (reference number of the main document unless explicitely mentionned) | Reviewer status: - Open - Closed
1 | Bernd Hekele |  | The document has different targets: - a technical part describing on low level the interfaces - a high-level API requirements section - a high-level API architecture section To handle the document according to this different level of detail I propose to split the document in peaces. | Clarify |  | n | Document | To be discussed. The current position of Alstom is to keep this document structure.
2 | Bernd Hekele |  | The definition of MMU_Counter is not consitent bewteen the two documents. | Accepted |  | y | Document | Please provide more detail. I see one inconsistency : the "acceleration" field is different; only the nominal value of the acceleration is used. | §4.7 modified : "Only the nominal value of the acceleration measure is available in the SW"
1 | Niklas Schaffrath |  | p12, first paragraph: Today,there is no definition of kernel and peripheral functions in ETCS. Different ETCS products distribute the function differently onto hardware components. The given API assumes the functional decomposition of the Alstom onboard solution, therefore making it only usuable with this platform. | Rejected | Design choice | n | System architecture
2 | Niklas Schaffrath |  | 1.2 The lifecycle of this document should not be coupled to the Alstom product development. | Clarify |  |  |  | Why? This sentence will be removed when the document will be fully baseline 3 compliant.
3 | Niklas Schaffrath |  | 1.3 This description implies some architectural decisions without explain them – telegrams, services… | Rejected | Design choice | n | System architecture | Please provide examples !
4 | Niklas Schaffrath |  | 1.3 ADA software source code is very specific for one onboard implementation | Rejected | Design choice | n | SW | can be discussed
5 | Niklas Schaffrath |  | 2.4 BTM, CORE, CPBI, CIE, CTE, GEOS, NOVRAM, RTM, SDMU – these are Alstom specific hardware components | Rejected | Design choice | n | Document | Those terms are to be understood according their general functionality ; E.g "BTM" : the module that will receive the balise telegram E.g GEOS : "the module that will execute the odometry computation" etc….
6 | Niklas Schaffrath |  | 2.4 EVC: Definition is missing. There is no agreed definition of this term. | Rejected | Design choice | n | System architecture | EVC is "European Vital Computer" indeed (see §2.4). I suppose your question is about the exact specification of the EVC.
7 | Niklas Schaffrath |  | 2.4 Remark: This might be acceptable for an intermediate state of the document, but must be corrected | Rejected | Design choice | n | Document | Unless there is confusion, we will keep it like that.
8 | Niklas Schaffrath |  | 3.2 First bullet: subset 26 defines no functional structure of the EVC, it names only "interface functions" to the ERTMS/ETCS onboard without giving subsystem borders. | Rejected | Design choice | n | System architecture
9 | Niklas Schaffrath |  | 3.2 second bullet: It is unclear why this Alstom interfaces are listed in the document. There is an undefined relation between the "for information" interfaces and the so called "OPEN ETCS Application functions". | Accepted |  | n | Document | Will be re-phrased like that : "Some of these "constructor specific" services will simply be listed for information only". | §3.2 modified
10 | Niklas Schaffrath |  | 3.2 The Open ETCS Application functions are undefined. | Rejected | Design choice | n | System architecture
11 | Niklas Schaffrath |  | 3.3.1 "CORE board" This is part of the Alstom hardware architecture and should not mentioned here. The distribution of the software on nodes should not be fixed here. | Rejected | Design choice | n | Document
12 | Niklas Schaffrath |  | 3.3.1 It is not necessary to define call directions, since this is an implementation details that arises from the fact that the assumed software technology implements data flows always with control flows. | Rejected | Design choice | n | SW
13 | Niklas Schaffrath |  | 3.3.1 "TYPES packages" software component: This component seems to origin from the Ada background. In general, it is unusual data types on interfaces are not modelled as "callable components". | Clarify |  | n | SW | To be discussed
14 | Niklas Schaffrath |  | 3.3.2 "peripheral board" The API description should be independed of the hardware architecture | Rejected | Design choice | n | Platform
15 | Niklas Schaffrath |  | 3.3.2 "Cycle": The API should not described from the viewpoint of the "Basic SW", as its function is outside of the scope. | Rejected | Design choice | n | SW
16 | Niklas Schaffrath |  | 3.3.3 The use of "calls" to "services" to implement data flows is specific to the Alstom Ada environment, the API should be based on data flows. | Rejected | Design choice | n | SW
17 | Niklas Schaffrath |  | 3.3.3 Diagram: The diagram is unclear, what does it mean that the tons are overlapping the "Application" oval? Are those arrows control flows or data flows? Also, it introduces a new component "Monitor", that was not mentioned before. | Accepted |  | n | Document | Clarification will be made: - Tons are overlapping the "application" because the in/out data memory buffers are implemented inside the application software component. - Arrows are control flows - the "monitor" is to be explained | §3.3.3 modified
18 | Niklas Schaffrath |  | 3.3.3 calling sequence: Is this an example? | Accepted |  | n | Document | Yes, it is an example. The calling order of the services can be changed. This drawing should not be taken in a "formal" way. This will be clarified in the document. | §3.3.3 modified
19 | Niklas Schaffrath |  | 3.3.3 page 16, paragraph starting with “The order” and following: This shows that the Alstom proposal of individual function calls instead of a data flow brings unnecessary complexity into the system. | Rejected | Design choice | n | Platform, SW | The "unecessary complexity" statement is not objective. Please could you provide more explanation ? For the principle, you could possibly send the input data at once at each cycle inside a single data structure (it would be equivalent to the Alstom choice). For the principle, you could possibly read the output data at once in each cycle inside a single data structure (it would be equivalent to the Alstom choice). What is important is that the different kinds of inputs provided in the current cycle are not ordered by the basic SW according to their ageing.
20 | Niklas Schaffrath |  | 3.3.3, page 16, paragraph starting with "For each...": This advice is out of the scope of the current document | Rejected | Design choice | n | Platform
1 | Uwe Steinke |  | 1.1: "This document is the ALSTOM proposal" : This statement is ok, if the document shall persist with this character. If it intended to become the openETCS API, it must be modified into a neutral openETCS document. | TBD |  | n | Document | Maybe to be changed later according to the future context.
2 | Uwe Steinke |  | 1.2: An unambiguous reference to the Unisig version should be given. | Accepted |  | n | Document | As written : "current status of the Alstom API for baseline 3, at the date of edition". It will be baseline 3 compliant in the future and then this text will be changed.
3 | Uwe Steinke |  | The document as a whole must be referenceable. "API Requirements for OpenETCS – V1.2" seems a little weak. | Clarify |  |  |  | ask suggestion
4 | Uwe Steinke |  | 3.1: The API and its location should be shown in the diagram. | Clarify |  |  |  | How ?
5 | Uwe Steinke |  | 3.1, "It does not cover the implementation of the peripheral functions and modules such as ...": An architectural overview should be provided to clarifiy which functions and features are located in the application SW, in the API, the Basic SW of the Core board and the peripheral function modules. | Rejected | Out of scope | n | System architecture
6 | Uwe Steinke |  | 3.1: "... notice that the API SW belongs to the Application SW component": What are the aim and the impact of this sentence? | Rejected | Answer provided | n | SW | Explain. From a SW architecture point of view, the API is part of the Application SW component. The BSW calls the ASW API.
7 | Uwe Steinke |  | 3.2: "services ... hat are specific to the implementation of some constructor (ALSTOM ..." : These services should be abstracted to become vendor-unspecific. | Rejected | Design Choice | n | SW
8 | Uwe Steinke |  | 3.3.1: "... the Basic Software is in charge of calling all services of the Application SW (through the API)" : Previously, it was stated that the API provides services for the application SW. Here it sounds the other way around. What is meant? | Rejected | Misunderstanding | n |  | Explain : The API SW is made of services. The API SW belongs to the ASW software component. The BSW calls the API services.
9 | Uwe Steinke |  | 3.3.2: Main phase "Failure : the normal working cycles shall be interrupted in case of failure (HW failure, System failure,…) detected by the Basic or the Application SW" : Which impact does this have on the application SW? What are the application SW requirements for this phase? | Accepted |  | n | Document | The explanation for the transition to "failure mode" will be improved. | §3.3.2 and §3.3.3 modified
10 | Uwe Steinke |  | 3.3.3: Diagram "API services": Each of the "WRITE_" functions must provide a consistent set of input data, that can be evaluated by the application software independently and - if neccessary - with usage of the input data stored from previous WRITE-functions within the same or former cycles, but without the need for the application to wait for subsequent "WRITE_" calls. | Rejected | Design Choice | n | Platform | Refer to our mail exchanges. To be discussed and also clarified in review meeting. It seems to be a totaly different phylosophy which is very difficult or impossible to implement. It would be easier to understand if you could provide examples of how you suggest to do.
11 | Uwe Steinke |  | 3.3.3: The Basic SW and the API must not require the application SW to sort its input data received via the "WRITE_" functions and to reconstruct the correct sequential and chronological order. | Rejected | Design Choice | n | Platform | Refer to our mail exchanges. To be discussed and also clarified in review meeting. It seems to be a totaly different phylosophy which is very difficult or impossible to implement. It would be easier to understand if you could provide examples of how you suggest to do.
12 | Uwe Steinke |  | 3.3.3: The Basic SW and the API must not require the application to store more than one input data set of the same "WRITE_" function type or more than one output data set of the same "READ_" function type within one cycle. Instead, the Basic SW and API are responsible for providing the appropriate FIFO buffers for input and output data. | Rejected | Design Choice | n | SW | Refer to our mail exchanges. To be discussed and also clarified in review meeting. This seems just a SW source code aspect.
13 | Uwe Steinke |  | 3.3.4: The worst case timing properties guaranteed to the application SW by the basic software are not specified. Examples: | - | - | - | - | - |  | -
14 | Uwe Steinke |  | * Worst case maximum propagation delay between an external event and its delivery to the application SW | TBD |  |  |  | See §3.3.5 : T_min, T_max. To be discussed.
15 | Uwe Steinke |  | * Guarantee to preserve the chronologically sequence between events | Rejected | Design Choice | n | Platform | The chronology is respected for each king of input separately. E.g chronology of balise reception is respected (§4.8.2.4). This principle is valid for each kind of input separately. I will check in the document if it is clear enough.
16 | Uwe Steinke |  | * The proceeding how the application software is able to produce a sequence of output events. | Clarify
17 | Uwe Steinke |  | * The warranty that the application software is not in due for debouncing input data or adhering to the sampling theorem. | TBD |  |  | Document | Refer to our mail exchanges. To be discussed and also clarified in review meeting. E.g More explanation in the document should be provided for the digital inputs sampling.
18 | Uwe Steinke |  | * The warranty that input data belonging together are delivered to the application software within the same cycle | Rejected | Design Choice | n | Platform | Refer to our mail exchanges. To be discussed and also clarified in review meeting.
19 | Uwe Steinke |  | 3.3.5: "the various peripheral boards/sub-systems in charge of the input/output treatment are not synchronised and that their performances are not identical, nor constant in time": This is ok for the peripherals itself. But the basic software must be in charge of isolating from (hardware) platform dependencies by synchronization and providing the correct order of inputs and outputs; otherwise, the application software would become hardware and platform dependant, which should be avoided. | Rejected | Design Choice | n | Platform | To be discussed. I am not sure to understand your "HW and platform dependancy" argument. It seems to be a totaly different phylosophy which is very difficult or impossible to implement. It would be easier to understand if you could provide examples of how you suggest to do.
20 | Uwe Steinke |  | 3.3.5: "the receiving applications may apply a correction in order to manage the delay of transmission of the data; assuming that the clocks of the various calculators are synchronised": This transfers the need for reordering and synchronization, caused by the underlying hardware platform, to the application software and makes it hardware and platform dependant. A hardware dependant application software contradicts the openETCS goals and must be avoided. | Rejected | Design Choice | n | Platform | To be discussed. I am not sure to understand your "HW and platform dependancy" argument. It seems to be a totaly different phylosophy which is very difficult or impossible to implement. It would be easier to understand if you could provide examples of how you suggest to do.
21 | Uwe Steinke |  | The Basis SW must be extended with synchronization and reordering capabilities instead. | Rejected | Design Choice | n | Platform
22 | Uwe Steinke |  | 4.1.1: "After treatment, the input stack is supposed to be empty.": what is the impact of an empty input stack? Where in the architecture resides the input stack? | Rejected | Answer provided | n |  | The input stack is inside the ASW software component. After ASW execution, input stack must be empty unless, at the next cycle, when the BSW will add new element, it could become full and generate an error (loss of events)
23 | Uwe Steinke |  | 4.1.1: Who is responsible to maintain the connection states of the peripherals: the basic SW or the application SW? | Rejected | Answer provided | n |  | The BSW.
24 | Uwe Steinke |  | 4.2.1: "The control interface allows the Basic SW to initialise and activate the application ..": Where in the architecture (see 3.2) it the control interface located? | Rejected | Answer provided | n | Document | On the upper left side of the drawing (initialisation, cyclic activation)
25 | Uwe Steinke |  | 4.2.4.4: How can the application SW generate a non-arbitrary sequence of outputs? | Clarify
26 | Uwe Steinke |  | 4.3.1: The functional data flows related to the configuration interface are not identifiable in "OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf". The search for "CONFIGURATION INTERFACE" in this document has no results. | Rejected | Out of scope | n |  | This is in the scope of the ETCS modeling
27 | Uwe Steinke |  | 4.3.2: PLUG_BIT_STREAM_T is not traceable to "OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf". | Accepted |  | n | document | It would be better to fill the §"functional data flow" for clearer traceability with the data dictionnary. Nevertheless, traceability is almost evident. | §4.3.1.1 and §4 (in general) modified
28 | Uwe Steinke |  | 4.3.2.4: "The parameters data will be provided in the form of a bit stream": The parameter data must be provided in a structured symbolic manner instead of a bit stream. Otherwise, the application software will become hardware and platform dependant. | Rejected | Design Choice | n | SW
29 | Uwe Steinke |  | 4.3.3.2: ETCS_ID_T is not traceable to "OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf". | Accepted |  | n | Document | It would be better to fill the §"functional data flow" for clearer traceability with the data dictionnary. Nevertheless, traceability is almost evident. | §4.3.1.1 and §4 (in general) modified See nid_engine in the appendix "data dictionnary
30 | Uwe Steinke |  | 4.4.3.2: PERMANENT_DATA_T is not traceable to "OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf" | Accepted |  | n | Document | It would be better to fill the §"functional data flow" for clearer traceability with the data dictionnary. Nevertheless, traceability is almost evident. | §4.4.2.1 and §4 (in general) modified see coded_data_restored_at_power_up in the appendix "data dictionnary
31 | Uwe Steinke |  | 4.4.4.4: "If it is the case, the train shall never be able to start again until new software is downloaded to restore a correct content to that Novram." It's unclear, which part of the sw is in charge for this function. Additionally, it is platform / hardware dependant since it requires collaboration with the NVRam store function. | Accepted |  | n | document | An explanation will be provided in the document. I don't understand your "platform / HW " argument. | modified: §4.4.1, §4.4.4, §4.4.6 and §4.4.8
32 | Uwe Steinke |  | 4.6.2.1: "The Application shall never use directly the Basic SW clock." What does this mean practically? | Rejected | Answer provided | n |  | The principle is that input data are provided by the BSW to the ASW. "TIME" is an input data. By experience in the past, some ASW developers have tried to use directly the real-time clock; which is contrary to the principle. This is the purpose of this text in the API document.
33 | Uwe Steinke |  | 4.7.2.4, first diagram: in a section of the diagram, the term (Distance(maximum) - Distance(nominal)) is decreasing. Is this a practical situation? | Rejected | Answer provided | n |  | Yes it is possible.
34 | Uwe Steinke |  | 4.8.2.4: "As long as the train is stopped over the balise, the telegram will not be provided to the application": Therefore, the application SW does not know about this position until the train leaves its position on the balise. Is this practically tolerable? | Rejected | Answer provided | n |  | Yes, according to Alstom, it is OK.
35 | Uwe Steinke |  | The API actually does not provide diagnosis functions. Therefore it must be extended by diagnosis functions like | - | - | - | - | - |  | -
36 | Uwe Steinke |  | *logging functions enabling the application software to write diagnosis information into a log file | TBD |  |  |  | The application can use the "ERROR_MANAGEMENT" service or the "DRU" service. But other services exist in the Alstom solution for logging; to be discussed.
37 | Uwe Steinke |  | *functions to observe the application software status (read status information provided for diagnosis purposes) | TBD |  |  |  | see above
38 | Uwe Steinke |  | *read and write application sw data (write enabled only while in test mode) | TBD |  |  |  | Is this linked to the use of a debugger tool?
39 | Uwe Steinke |  | *halt and resume functions for the application sw (enabled only while in test mode) | clarify
40 | Uwe Steinke |  | The documents OETCS_API Requirements_v1.2.pdf, OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf, OETCS_API Requirements_appendix_application_layer_v1.0.pdf should be delivered in an editable format additionally. | Accepted |  | n | Document | The editable formats have been provided according to your demand. | done
41 | Uwe Steinke |  | In addition to the documents, the API by any means must be extended with a (formal) machine-readable interface description for the API data types and the API functions (SysML, XML, openETCS data dictionary format, ..). It will be required for the integration between API and application SW anyway. It is expected that this formal interface description is able to replace the OETCS_API Requirements_appendix_functional_data_dictionary_v1.0.pdf, OETCS_API Requirements_appendix_application_layer_v1.0.pdf documents completely. | Rejected | Out of scope
42 | Uwe Steinke |  | The duties of the Basic SW and the application SW must be separated more clearly. | Clarify
43 | Uwe Steinke |  | The requirements to the application SW and the Basic SW must be listed in a traceable format and supplied with unique requirement IDs. | Rejected | Out of scope
44 | Uwe Steinke |  | The upper layer of the Basic Software must be specified with the API as well, since the implementation of the API requires the implementation of the Basic SW on non-Alstom platforms. | Clarify
45 | Uwe Steinke |  | The Basic SW must preserve the sequence of input events to the application SW and the sequence of output events from the application SW. If the used hardware does not preserve the correct order (that it is a hardware characteristic), the Basic SW must keep the application away from hardware dependencies and reconstruct the order before applying them to the application. | Rejected | Design Choice | n | Platform | See comments above in this sheet.
46 | Uwe Steinke |  | Separation of concerns: The architecture must be given specifying clearly, which of the OBU subfunctions are allocated to | Rejected | Design Choice | n | System architecture
47 | Uwe Steinke |  | * the application SW | - | - | - | - | -
48 | Uwe Steinke |  | * the Basic SW and the underlying hardware | - | - | - | - | -
49 | Uwe Steinke |  | The timing restrictions (300 ms cylce period, 1 ms clock synchronization accuracy, delays, ..) are closely related to the special underlying hardware platform. These imply restrictions to SW portabiltiy. | Rejected | Design Choice | n | Platform
50 | Uwe Steinke |  | In general, the API and the Basic SW need to be split into layers: | Clarify
51 | Uwe Steinke |  | * into an abstraction layer with as little platform and hardware dependancies as possible | Clarify
52 | Uwe Steinke |  | * into underlying components with clearly defined capabilties
1 | eric schellenberg | main document | General | - | - | - | - | - |  | -
2 | eric schellenberg | main document | For a better visibily, the functional data flow for each interface should be indicated in the main document. | Accepted |  | n | document | It would be better. | §4 modified
3 | eric schellenberg | main document | But this functional data flow is not necessary if the parameters of services are detailed. | Clarify
4 | eric schellenberg | main document | General | - | - | - | - | - |  | -
5 | eric schellenberg | main document | The parameters of services should be detailed. | Clarify |  |  |  | See the functional data dictionnary or the ADA source code extract? (package TYPES should be provided ?)
6 | eric schellenberg | main document | General | - | - | - | - | - |  | -
7 | eric schellenberg | main document | There is no §6 in the document /2/ API Requirement for OpenETCS – appendix - Functional Data Dictionary, v1.0 | accepted |  | n | document | There is a §6 in the present document. This §6 points towards the appendix 2 file. The document could be changed to avoid any confusion. | Links to §6 have been modified
8 | eric schellenberg | main document | General | - | - | - | - | - |  | -
9 | eric schellenberg | main document | Parts SW API extract (ADA source code) should be moved in another document (appendix) | rejected | Design Choice | n | document
10 | eric schellenberg | main document | 2.1 / 2.2 | - | - | - | - | - |  | -
11 | eric schellenberg | main document | There is no difference between the references. | Accepted |  | n | document | It will be modified | §2 modified
12 | eric schellenberg | main document | Ie: | - | - | - | - | -
13 | eric schellenberg | main document | /1/ System Requirements Specification, ref. SUBSET-026, v3.3.0 | - | - | - | - | -
14 | eric schellenberg | main document | and | - | - | - | - | -
15 | eric schellenberg | main document | /1/ API Requirements for OpenETCS – appendix - Application layer, v1.0 | - | - | - | - | -
16 | eric schellenberg | main document | 2.1 | - | - | - | - | - |  | -
17 | eric schellenberg | main document | Some reference documents must be added. ie: | TBD |  |  |  | Basicly, only the subset26 of the baseline 3 is referred. The other subsets should implicitely be referred.
18 | eric schellenberg | main document | FIS Juridical Recording, ref SUBSET-027, v3.0.0 | Accepted |  | n | document | Could be referred because the format of the ETCS application output to JRU (ONLY for the DATA part; not the CONTROL part) respects the subset. | §2 and §4 modified
19 | eric schellenberg | main document | FFFIS STM Application Layer, ref SUBSET-058, v3.0.0 | Accepted |  | n | document | Could be referred because the format of the ETCS application output to STM (ONLY for the DATA part; not the CONTROL part) respects the subset | §2 and §4 modified
20 | eric schellenberg | main document | ETCS DRIVER MACHINE INTERFACE, ref ERA_ERTMS_015560, v3.3.0 | TBD |  | n | document | Could be referred because the format of the ETCS application output to STM respects this document. It is in reference of the appendix "application layer"
21 | eric schellenberg | main document | 4.2.3 | - | - | - | - | - |  | -
22 | eric schellenberg | main document | What are the parameters of service INITIALIZE? | rejected | answer provided | n |  | There are none. You probably want to refer to WRITE_CONFIG_DATA.
23 | eric schellenberg | main document | 4.3.1.2 | - | - | - | - | - |  | -
24 | eric schellenberg | main document | There is no output. Confirmed as there is no service like READ_CONFIG_DATA. | Accepted |  | y | document | The output § will be removed | §4 modified
25 | eric schellenberg | main document | 4.3.2 | - | - | - | - | - |  | -
26 | eric schellenberg | main document | The parameters of WRITE_CONFIG_DATA should be detailed. | Rejected | Out of Scope | n | System Architecture | To be defined by the OpenETCS model.
27 | eric schellenberg | main document | We think that the following data blong to these parameters: | - | - | - | - | see above
28 | eric schellenberg | main document | ETCS ID (subset-026, NID_ENGINE) | - | - | - | - | see above
29 | eric schellenberg | main document | Fixed data (subset-026, A3.1) | - | - | - | - | see above
30 | eric schellenberg | main document | Default national data (subset-026, A3.2) | - | - | - | - | see above
31 | eric schellenberg | main document | Traction model, braking model, brakes configuration, on-board correction factors, ... (subset-026, 3.13,2.2.2) ... | - | - | - | - | see above
32 | eric schellenberg | main document | 4.3.3 | - | - | - | - | - |  | -
33 | eric schellenberg | main document | Why a specific service for ETCS ID. It should be part of the configuration parapeters sends by WRITE_CONFIG_DATA. | Rejected | Design Choice | n | SW | Designer choice.
34 | eric schellenberg | main document | 4.4 | - | - | - | - | - |  | -
35 | eric schellenberg | main document | We understand that the permanent data are the data stored when the system is powered-off. Then, it should correspond to data unchanged when entering in NP mode (subset-026, 4.10): | Rejected | Out of Scope | n | System Architecture | To be defined by the OpenETCS model.
36 | eric schellenberg | main document | national values | - | - | - | - | see above
37 | eric schellenberg | main document | EOLM information | - | - | - | - | see above
38 | eric schellenberg | main document | Train position | - | - | - | - | see above
39 | eric schellenberg | main document | ERTMS/ETCS level | - | - | - | - | see above
40 | eric schellenberg | main document | Table of priority of trackside supported levels | - | - | - | - | see above
41 | eric schellenberg | main document | Radio Network ID | - | - | - | - | see above
42 | eric schellenberg | main document | RBC ID/Phone Number | - | - | - | - | see above
43 | eric schellenberg | main document | Operated System Version | - | - | - | - | see above
44 | eric schellenberg | main document | Virtual Balise Covers | - | - | - | - | see above
45 | eric schellenberg | main document | Language used to display information to the driver | - | - | - | - | see above
46 | eric schellenberg | main document | 4.4 | - | - | - | - | - |  | -
47 | eric schellenberg | main document | What is the criteria to set a permanent data as protected? | rejected | answer provided | n |  | A protected permanent data cannot not be erased or modified by the maintenance tool. (e.g wheel diameters) The maintenance tools allows to read and reset the NOVRAM "diagnose" data but it cannot be used to enter the protected permanent data nor to erase them. Entering the protected permanent data is a safe data entry process.
48 | eric schellenberg | main document | 4.4.5.2 | - | - | - | - | - |  | -
49 | eric schellenberg | main document | The parameters of READ_PERMANENT_DATA should be identical to the parameters of WRITE_PERMANENT_DATA | Clarify |  |  |  | They are not ? (PERMANENT_DATA_T)
50 | eric schellenberg | main document | 4.4.6.2 | - | - | - | - | - |  | -
51 | eric schellenberg | main document | The parameters of READ_PROTECTED_PERMANENT_DATA should be identical to the parameters of WRITE_PROTECTED_PERMANENT_DATA | Clarify |  |  |  | They are not ? (PROTECTED_PERMANENT_DATA_T)
52 | eric schellenberg | main document | 4.5.2 | - | - | - | - | - |  | -
53 | eric schellenberg | main document | To follow the naming philosophy, POWER_UP_TESTS_FINISHED should be renamed in WRITE_POWER_UP_RESULTS | rejected | Design Choice | n | document | Your remark is right but it is minor (no confusion). So we don't want to change the source code.
54 | eric schellenberg | main document | 4.5.3 | - | - | - | - | - |  | -
55 | eric schellenberg | main document | 4.5.4 | - | - | - | - | - |  | -
56 | eric schellenberg | main document | Why specific test services for BTM and not for other components? | rejected | Design Choice | n | SW
57 | eric schellenberg | main document | 4.6 | - | - | - | - | - |  | -
58 | eric schellenberg | main document | A service to provide local time is missing. It is necessary for some functions, ie: display of local time on DMI (ERA_ERTMS_015560, 8.4.3) | rejected | Design Choice | n | SW | Local time input: in the service "write_jru_message" Local time output to DMI : in the service "read_MMI_message"
59 | eric schellenberg | main document | 4.7.2 | - | - | - | - | - |  | -
60 | eric schellenberg | main document | The time of the measure should not be necessary. The OpenETCS SW needs the current odometric data and as all inputs will be provided at the same time, the current time is provided by service WRITE_TIME. | rejected | Misunderstanding | n | Platform | The timestamp of the odometry is not equal to the current time.
61 | eric schellenberg | main document | The estimation of the current odometric data should be be performed by the Application SW (OpenETCS) but by the Basic SW. | clarify
62 | eric schellenberg | main document | The provided Acceleration data must be safe as it is used in the calculation of EBI supervision limit (subset-026, 3.13.9.3.2.8) | rejected |  |  |  | The acceleretion data is not a safe data. This has been clarified at the Unisig.
63 | eric schellenberg | main document | 4.7 | - | - | - | - | - |  | -
64 | eric schellenberg | main document | Additionnal services are necessary to reset the confidence interval and to request odometry correction due to linking information. | rejected | Design Choice | n | System Architecture | This is to be managed by the Application
65 | eric schellenberg | main document | 4.8.4 | - | - | - | - | - |  | -
66 | eric schellenberg | main document | We think that the bad balise information should also be provided by the service WRITE_BTM_INFO in order to keep the sequence of balise reception when several balise are received in a cycle. | Accepted |  | n | SW | This is a good suggestion. Currently, this has no impact on the Alstom solution because this service is not used. But the improvement could be foreseen later.
67 | eric schellenberg | main document | 4.8.5 | - | - | - | - | - |  | -
68 | eric schellenberg | main document | As OpenETCS deals only with EuroBalise, the modulation information could be removed. | Rejected | Design Choice | n | System Architecture | Subset 36 says that the reception of KER balises is optional
69 | eric schellenberg | main document | For naming consistency, the service should be renamed in READ_BTM_ANTENNA as it allows to set the used antenna (and WRITE_BTM_ANTENNA allows to know the used antenna). | Rejected | Design Choice | n | Document | Your remark is right but it is minor (no confusion). So we don't want to change the source code.
70 | eric schellenberg | main document | 4.8.6 | - | - | - | - | - |  | -
71 | eric schellenberg | main document | To follow the naming philosophy, the service should be renamed in READ_METAL_MASS_INFO | Rejected | Design Choice | n | Document | Your remark is right but it is minor (no confusion). So we don't want to change the source code.
72 | eric schellenberg | main document | 4.9.3 | - | - | - | - | - |  | -
73 | eric schellenberg | main document | To follow the naming philosophy, the service should be renamed in READ_SS_CODE_FOR_LOOP | Rejected | Design Choice | n | Document | Your remark is right but it is minor (no confusion). So we don't want to change the source code.
74 | eric schellenberg | main document | 4.10 | - | - | - | - | - |  | -
75 | eric schellenberg | main document | In order to avoid unnecessary coding/decoding functions implementation in the application SW (OpenETCS), all TIU packets should be replaced by a corresponding service. | Rejected | Design Choice | n | SW
76 | eric schellenberg | main document | 4.10.5 | - | - | - | - | - |  | -
77 | eric schellenberg | main document | This service should be removed as the information is already provided by CCPU_EB_COMMAND (Application layer, 5.2.3 packet 0) | Accepted |  | n | Document | Both services achieve the same action and both have to be used by the application SW. The "EB_REQUEST" service request a high priority treatment by the Basic Software. This will be written in the API document. | §4.10.5 modified
78 | eric schellenberg | main document | 4.10.6 | - | - | - | - | - |  | -
79 | eric schellenberg | main document | This service should be removed as the information is already provided by V_TIU_ISOLATION_STATE (Application layer, 5.2.2 packet 0) | Rejected | Misunderstanding | n |  | The V_TIU_ISOLATION_STATE is the isolation request input from the TIU to the CORE ASW board. The service EVC_ISOLATION_REQUESTED provides the information to the Basic SW.
80 | eric schellenberg | main document | 4.10.7 | - | - | - | - | - |  | -
81 | eric schellenberg | main document | This service should be removed as the information is already provided by V_TIU_DESKS_STATE (Application layer, 5.2.2 packet 0) | Rejected | Misunderstanding | n |  | The V_TIU_DESK_STATE is the desk state input from the TIU to the CORE ASW board. The "OCCUPIED_CABIN" service provides the information to the Basic SW.
82 | eric schellenberg | main document | 4.11.1.3 | - | - | - | - | - |  | -
83 | eric schellenberg | main document | DMI interface is described in §3 of appendix 1 | Accepted |  | n | document | This §6 points towards the appendix 1 file. It can be modified to avoid confusion. | modified
84 | eric schellenberg | main document | 4.12.1.3 | - | - | - | - | - |  | -
85 | eric schellenberg | main document | JRU interface is described in §4 of appendix 1 | Accepted |  | n | document | This §6 points towards the appendix 1 file. It can be modified to avoid confusion. | modified
86 | eric schellenberg | main document | 4.12 | - | - | - | - | - |  | -
87 | eric schellenberg | main document | The interface could be limited to the service READ_JRU_MESSAGE and JRU_MESSAGE_QUEUE_IS_EMPTY. | Rejected | Design Choice | n | SW | The ETCS application receives inputs from the JRU service: - UTC time, Local time,.. - control data (JRU state)
88 | eric schellenberg | main document | The parameter of READ_JRU_MESSAGE should be limited to the JRU message defined in subset-027 v300 | Rejected | Design Choice | n | System Architecture | The JRU output service sends "data messages and "control messages" to the JRU. "Data messages" are in the format specified by the subset 27. The EVC output baseline 3 to Crash Protected Memory is compliant subset 27 baseline 3.
89 | eric schellenberg | main document | 4.13.2 | - | - | - | - | - |  | -
90 | eric schellenberg | main document | 4.13.3 | - | - | - | - | - |  | -
91 | eric schellenberg | main document | The parameter of WRITE_STM_MESSAGE and READ_STM_MESSAGE should be limited to the STM message defined in subset-058 v300 | Rejected | Design Choice | n | System Architecture | The OpenETCS "STM services" include "data messages" and "control messages". The data messages are compliant to the subset 58.
92 | eric schellenberg | main document | 4.13.5 | - | - | - | - | - |  | -
93 | eric schellenberg | main document | What is the purpose of this service? | Accepted |  | n | document | STM_INFO is for Alstom specific purpose (diagnose) | modified
94 | eric schellenberg | main document | 4.14.3 | - | - | - | - | - |  | -
95 | eric schellenberg | main document | What is the purpose of this service? | Rejected | Design Choice | n | System Architecture | WRITE_MOBILE_CONTEXT. The BSW knows the context of the Mobile and provides it to the application.
96 | eric schellenberg | main document | The mobile context could be stored as the radio session status and this service is not necessary. | Rejected | Misunderstanding | n
97 | eric schellenberg | main document | 4.14..4.4 | - | - | - | - | - |  | -
98 | eric schellenberg | main document | The following messages are missing: | - | - | - | - | - |  | -
99 | eric schellenberg | main document | NETWORK_LIST_REQUEST: to request the list of available radio network to display on DMI | TBD |  |  |  | The comment is right. Could be implemented in the frame of baseline 3.
100 | eric schellenberg | main document | CONNECTION_RESPONSE: to answer to a connection indication when the connection is performed on RBC initiative. | TBD |  |  |  | The comment is right. The Alstom Onboard ETCS does not manage the call from the RBC.
101 | eric schellenberg | main document | 4.14.6.4 | - | - | - | - | - |  | -
102 | eric schellenberg | main document | The following messages are missing: | - | - | - | - | -
103 | eric schellenberg | main document | NETWORK_LIST: to provide the list of available radio network | TBD |  |  |  | The comment is right. Could be implemented in the frame of baseline 3.
104 | eric schellenberg | main document | CONNECTION_INDICATION: to indicate that connection has been performed on RBC initiative | TBD |  |  |  | The comment is right. The Alstom Onboard ETCS does not manage the call from the RBC.
105 | eric schellenberg | main document | 4.14.7 | - | - | - | - | - |  | -
106 | eric schellenberg | main document | What is the purpose of this service as the management of radio hole should be performed by the application SW (OpenETCS)? | Rejected | Design Choice | n | System Architecture | This function is achieved by the Application and the Basic SW.
107 | eric schellenberg | main document | This service should be removed. | - | - | - | - | -
108 | eric schellenberg | main document | 4.15 | - | - | - | - | - |  | -
109 | eric schellenberg | main document | We don't understand the purpose of Event report. | Rejected | answer provided | n |  | This service is useful because only the application SW is able to code a telegram to the DMI (but also to STM, RBC, JRU, etc…) according the subset languages (subset 58, subset 27, ..). So if an BSW event has to sent to DMI (STM, JRU, ….); it has to be provided by the BSW to the ASW using this service.
110 | eric schellenberg | main document | The example about display of text on DMI is not applicable as it is managed by 4.11 | - | - | - | - | - |  | -
111 | eric schellenberg | application layer | 3 | - | - | - | - | - |  | -
112 | eric schellenberg | application layer | It would be useful to have a summary list of DMI packets | Accepted |  | n | document | We will take into account the suggestion. (later)
113 | eric schellenberg | application layer | 3 | - | - | - | - | - |  | -
114 | eric schellenberg | application layer | This application layer seems to be at very low level. It means that a lot of DMI functionalities will have to be implemented in the Application SW (OpenETCS), most of requirements in ERA_ERTMS_015560 have to be taken into account in OpenETCS SW. | Rejected | Design Choice | n | System Architecture
115 | eric schellenberg | application layer | 3 | - | - | - | - | - |  | -
116 | eric schellenberg | application layer | Due to this low level application layer, the description of the packets/variables is not sufficient. A complete specification of the packets usage with the expected behaviour of the corresponding DMI is requested. | Rejected | Design Choice | n | System Architecture
117 | eric schellenberg | application layer | 3.3 | - | - | - | - | - |  | -
118 | eric schellenberg | application layer | Packets for management of text messages seems to be redundant: | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
119 | eric schellenberg | application layer | Packet 78 = 02 : delete text message | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
120 | eric schellenberg | application layer | Packet 66 = 09: display text message | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
121 | eric schellenberg | application layer | Packet 77 = 50: ack text | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
122 | eric schellenberg | application layer | Packet 79 = 56: stack full | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
123 | eric schellenberg | application layer | In order to clarify/simplify the data exchanged, it should be possible to use only one improved set of packets (indicating if the text is related to EVC, track or STM) | Rejected | Design Choice | n | System Architecture | Your suggestion is not wrong but a different choice has been made by Alstom.
124 | eric schellenberg | application layer | 4 | - | - | - | - | - |  | -
125 | eric schellenberg | application layer | JRU interface should be limited to the JRU messages defined in subset-027 v300. | Rejected | Design Choice | n | System Architecture | see you comment about §4.12
126 | eric schellenberg | application layer | Time information is provided by the Time Interface of API and status provided by Tests interface. | Rejected | Design Choice | n | System Architecture | see you comment about §4.12
127 | eric schellenberg | application layer | 5.2.2 | - | - | - | - | - |  | -
128 | eric schellenberg | application layer | Packet 0: | - | - | - | - | - |  | -
129 | eric schellenberg | application layer | V_TIU_TILTING_STATE_FILTERED and V_TIU_TILTING_STATE are not used by ETCS. | Rejected | Design Choice | n | System Architecture | Your remark is correct. However, Alstom decided to keep this information available. (Was existing in previous versions of SUBSET-034)
130 | eric schellenberg | application layer | V_TIU_VIGIL_ACTION_STATE_FILTERED, V_TIU_VIGIL_DISABLE_STATE_FILTERED, V_TIU_VIGIL_ACTION_STATE and V_TIU_VIGIL_DISABLE_STATE are not used by ETCS. | Rejected | Design Choice | n | System Architecture | Your remark is correct. However, Alstom decided to keep this information available. (Was existing in previous versions of SUBSET-034)
131 | eric schellenberg | application layer | Information about status of special brakes (regenerative brakes, magnetic shoe brakes, eddy current brakes, ...), passive shunting, pneumatic brake pressure, Type of train data entry are missing (see subset-034) | TBD
132 | eric schellenberg | application layer | 5.2.2 | - | - | - | - | -
133 | eric schellenberg | application layer | Packet 1 and 2: text from TIU is out of ETCS scope | Rejected | Design Choice | n | System Architecture | Your remark is correct. However, Alstom decided to keep this information available.
134 | eric schellenberg | application layer | 5.2.2 | - | - | - | - | -
135 | eric schellenberg | application layer | Packet 3 is not necessary if braking model is part of the configuration interface. | Accepted |  | y | document | Your remark is correct. The API document v1.2 is not yet fully compliant to Baseline 3. This information is now removed from TIU parameters and moved to the configuration interface. The API document will be updated.
136 | eric schellenberg | application layer | 5.2.2 | - | - | - | -
137 | eric schellenberg | application layer | Packet 6 and 12 are not necessary if test and status of components are part of Tests interface. | Rejected | Design Choice | n |  | Your remark is correct. However, Alstom decided to implement it in this way.
138 | eric schellenberg | application layer | 5.2.2 | - | - | - | - | -
139 | eric schellenberg | application layer | Packet 7 and 8: what is the purpose of these packets? | Accepted |  | n | document | Packet 7: This is related to the management of the TI and BI units for STM interfaces. Packet 8: This is specific information implemented by Alstom for a dedicated project. (This will be clarified in the API document) | appendix "Application layer" modified. (§5.2.2)
140 | eric schellenberg | application layer | 5.2.2 | - | - | - | - | -
141 | eric schellenberg | application layer | Packet 13: what is the purpose of this packet? | Accepted |  | n | document | This is specific information implemented by Alstom for a dedicated project. (This will be clarified in the API document) | appendix "Application layer" modified. (§5.2.2)
142 | eric schellenberg | application layer | 5.2.3 | - | - | - | - | -
143 | eric schellenberg | application layer | Packet 0: | - | - | - | - | -
144 | eric schellenberg | application layer | CCPU_VIGIL_DISABLE_ORDER is not used by ETCS | Rejected | Design Choice | n | System Architecture | Your remark is correct. However, Alstom decided to keep this information available. (Was existing in previous versions of SUBSET-034)
145 | eric schellenberg | application layer | 5.2.3 | - | - | - | - | -
146 | eric schellenberg | application layer | Packet 3 and 4: what is the purpose of these packets? | Accepted |  | y | document | Packet 3: Alstom decided to make this information available. Packet 4: The API documents v1.2 is not yet fully complinant to Baseline 3. This information is now removed from TIU. The API document will be updated. (will be updated later when baseline 3 implementation will be stable)
147 | eric schellenberg | application layer | 5.2.3 | - | - | - | - | -
148 | eric schellenberg | application layer | Packet 6: is this packet used for odometer recalibration? If yes, it should be part of MMU interface. | Rejected | Misunderstanding | n |  | No. However Alstom decided to make this information available.
149 | eric schellenberg | application layer | 5.2.3 | - | - | - | - | -
150 | eric schellenberg | application layer | Packet 7,8 and 9: what is the purpose of these packets? | Rejected | Design Choice | n |  | Packet 7: Alstom decided to make this information available. Packet 8: This is related to the management of the TI and BI units for STM interfaces. Packet 9: Alstom decided to make this information available.
151 | eric schellenberg | application layer | 5.2.3 | - | - | - | - | -
152 | eric schellenberg | application layer | There is no packet for Change of allowed current consumption | Accepted |  | y | document | Still to be developed. (Was not yet defined at the time of writing the API documentation v.1.2)
153 | eric schellenberg | data dictionnary | We think that it is difficult to use the information in this document in its current state. | TBD |  | n | document
154 | eric schellenberg | data dictionnary | Furthermore, if the parameters of API services are detailed in the document "OETCS API Requirements", this document is not necessary. | clarify
1 | GEVincent |  | general: GE platform uses C code and not ADA; To be discussed we propose API based on the POSIX 2.0 interface layer. Advantages would be that the interface is standard and has its own documentation. Only work would be to clarify which POSIX interface calls will be supported | Rejected | Design Choice | n | SW | can be discussed.
2 | GEVincent |  | 3.3.1: For the "types" to use: could be important to limit the use to certain types: for example, prevent the use of floating point (safety reason) | TBD |  | n | SW | to be discussed : are "Coding rules" part of the API?
3 | GEVincent |  | 3.3.4: "The duration of the CORE board cycle does not have to be constant": the duration of the CORE board cycle for GE platform is constant. To be discussed | Rejected | Design Choice | n | Platform | The duration of the CORE board does not have to be constant, but it can be constant. (so it is flexible : it can be constant or not). This additionnal text could be added in the API for better understanding.
4 | GEVincent |  | 4.4.6: "As these data CANNOT be erased by the maintenance team, the Application SW must ensure that their decoding shall not kill the EVC." = what is the exact meaning of this sentence? how to do that? | Accepted |  | n | Document | Explanation : When decoding the Novram data, the application SW should use "defensive programming" so that in case of inconsistent non-volatile memory data (e.g the version of the data structure is not good) , it will not crash the SW. Instead, it should continue with "default values", or prompt for a new data entry on the DMI, etc ... This is even more important for the NOVRAM area which is "protected" because in that case, the service tool of the EVC can't reset the NOVRAM data. This additional explanation should be added in the API document. | modified: §4.4.1, §4.4.4, §4.4.6 and §4.4.8
5 | GEVincent |  | 4.5.2.1: JRU and DMI can also be tested automatically when powered up | Rejected | Answer provided | n |  | yes, but these DMI (TRU) tests are achieved in parallel with those of the EVC. The EVC is aware of the DMI (TRU) selftest results only when the interface EVC-DMI (EVC-TRU) is established.
6 | GEVincent |  | 4.6.2: is it a vital clock or non vital clock? Don't we need also a non vital clock for maintenance event timestamp or to manage MDI clock? | Clarify |  | n |  | This is a vital clock. Yes, a non-vital clock could also be used for diagnose purpose. To be discussed. What is a MDI clock?
7 | GEVincent |  | 4.7.2: Is there any odometry algorithm application running outside the application software? On the GEOS board? Is the odometry algorithm potentailly one of the development of the OpenETCS? | Rejected | Answer provided | n |  | Yes: an odometry algo is running on the GEOS board outside the ETCS application scope. This algorithm is constructor dependant and is not part of the OpenETCS perimeter.
8 | GEVincent |  | 4.7.2.2: is TIME-STAMP = T_ODO as defined in SS? | Rejected | Answer provided | n |  | You mean the subsets 58? The EVC safe clock is the reference clock of the EVC node/ A reference to §4.6.2 could be added in the API text.
9 | GEVincent |  | 4.8.2.4: "The position of the center of the balise will be provided in the same coordinate system as the MMU distance calculation": is it possible to clarify what is the possible coordinate system? | Rejected | Answer provided | n |  | A reference to §4.6.2 could be added in the API text.
10 | GEVincent |  | 4.9: GE platform doesn't support Euroloop. Is it part of the OpenETCS ? | TBD |  | n |  | I suppose that it is part of Open ETCS; maybe optionnal ?
11 | GEVincent |  | 4.10: EB_requested, EVC_isolation_is_requested, occupied_cabin: why does the document detail only these TIU and not others from SS034? | Rejected | Design Choice | n | SW | A designer choice is to have separate services for some digital I/Os. The other digital I/Os are available through the TIU messages.
12 | GEVincent |  | 4.13: can you confirm that the aplication SW is providing messages as described in SS058. lower layers (SL/STL/Profibus) are services of the Basic SW? | Accepted |  | n | Document | Yes. Your text is right. It should be more explicit in the API text. | modified
13 | GEVincent |  | 4.14: Euroradio: confirm that the SS037 is implemented in the Basic SW? | Rejected | Answer provided | n |  | Yes.SS037 is implemented in the Basic SW.
1 | C.Giraud (Als) | 3.1 | The drawing of chapter 3.1 should include EVC, the CORE board and the CAN bus that permits communication between modules. | Rejected | Misunderstanding | n | Document | I suggest not to enter into alstom internal architecture details * voir l'autre diag du §3.1
2 | C.Giraud (Als) |  | The definition of Odo_Counter is not consitent : how is achieved synchro with BTM? | Clarify |  | n | System Architecture | * Please explain why "Odo_counter is not consistent" ? * in the next version of the document, for better understanding, it will be added "When passing over a balise, the reset of the error range ¦Distance_max – Distance_min¦ is to be managed by the application". | §4.7 (main document)
3 | C.Giraud (Als) | 3.3.1 | For "integer" type, we needs to define the meaning of one bit : meter, m/s, m/s² or sub-multiple. Is there "floating point" ? | Accepted |  | n | Platform | * range, resolution, unit are provided in the appendix data dictionnary. This will be explicitly mentionned in the next version of the document * Floating point calculation must be supported by the platform (either by HW or by SW) | §3.3 (main document).
4 | C.Giraud (Als) | 3.3.4 | It seams that cycle duration is variable ? Can we define an average value ? | Rejected | Answer provided | n | Platform | Refer to our call-conf of 20/6/2014
5 | C.Giraud (Als) | all | On a general point of view, it seams reasonable and realistic to reduce the scope of Open ETCS to a minimum : input are balise and odometry, ouput are breaking curve and DMI interface. Braking Curves at each signal should appear as undeniable for validation of both generic and specific software (?). | TBD |  | n | System Architecture | to be discussed
***** | ***** | ***
Status (all to be agreed with reviewer)
| Accepted |  | 31
| Clarify |  | 20
| TBD |  | 17
| Rejected |  | 93
| total |  | 161
| Defect |  | 5
| No defect |  | 126
| autre (tbd, clarify, ..) |  | 30
| total |  | 161
Accepted
| Document |  | 30
| SW |  | 1
| Platform |  | 0
| System Architecture |  | 0
Rejected
| Design choice |  | 63
| Misunderstanding |  | 6
| out of scope |  | 6
| answer provided |  | 14
Topic
| Document |  | 44
| SW |  | 18
| Platform |  | 15
| System Architecture |  | 31
| autre (tbd, clarify, ..) |  | 53
| total |  | 161